## Read Me
Template K: Month-End Close Checklist
Free template from sachinnagpal.in ¦ Macro-free ¦ All sample figures are ILLUSTRATIVE ONLY
IMPORTANT DISCLAIMER: For computation and reconciliation assistance only; not a substitute for formal statutory audit or legal tax advice. All sample data in this file is made up for illustration and does not relate to any real company, trust or person. Rates, limits and rules must be checked against the current law and your own accounting policies before use. No tax saving, audit outcome or compliance result is promised.
What this template does
A ready-made month-end close calendar for a finance team, with tasks typical of an infrastructure / toll road company and an InvIT group. Each task has an owner, a reviewer and a working day (for example WD+2 = second working day after month-end). The template turns working days into real dates (skipping weekends and your holiday list), tracks status, flags overdue items and shows progress by area.
How to use it (step by step)
Step 1 | Go to 'Settings'. Type the month-end date you are closing (for example 30-Sep-2026) and the 'as of' date (today's date when you update the file). Type your holidays in the list.
Step 2 | Go to 'Checklist'. Review the sample tasks. Change, delete or add tasks; for each one choose the area, type the owner and reviewer, and the working day: 0 = last working day of the month, 1 = first working day after month-end, -1 = one working day before, and so on.
Step 3 | As work progresses, change 'Status' (Not started, In progress, Done, Not applicable) and type the completion date.
Step 4 | Overdue tasks and tasks done late are highlighted. The 'Dashboard' tab shows % complete by area and overall.
Step 5 | Save a copy for each month (for example Close-Sep-2026.xlsx) to keep an audit trail.
Tabs in this file
Settings | Month-end date, as-of date and holidays.
Checklist | Tasks with area, owner, reviewer, working day, due date, status and flags.
Dashboard | Progress by area and overall.
Colour code
1,00,000 | Yellow cell with blue text = an input. Type over it with your own data.
1,00,000 | Black text = a formula. Do not type over it; it updates by itself.
1,00,000 | Green text = a figure pulled from another tab.
OK | Checks area: every check should read OK. If one reads CHECK, something does not add up.
Assumptions and limits
• | Due date for working day N (N of 1 or more) = WORKDAY(month-end, N, holidays). For N of 0 or less it counts back from the last working day of the month.
• | Weekends are Saturday and Sunday. If your office works Saturdays, replace WORKDAY with WORKDAY.INTL in the 'Due date' column.
• | Overdue = not Done / Not applicable and the 'as of' date is after the due date. The file uses an 'as of' date that you type rather than TODAY(), so it does not change every time it is opened and saved copies stay as they were.
• | Capacity: 150 tasks and 40 holidays.
Version | v1.0, October 2026. Works in Excel 2010 or later, Excel for Microsoft 365, LibreOffice and Google Sheets. Amounts in Indian Rupees (₹).

## Settings
Settings
For computation and reconciliation assistance only; not a substitute for formal statutory audit or legal tax advice.
Month-end being closed |  | 2026-09-30
As-of date (today) |  | 2026-10-08
Last working day of the month |  | 2026-09-30
Holidays
| 2026-10-02 | Sample holidays only. Use your company's holiday list.
2026-10-20
2026-11-09
2026-12-25

## Checklist
Month-End Close Checklist
For computation and reconciliation assistance only; not a substitute for formal statutory audit or legal tax advice.
Sample tasks are illustrative. Owners are placeholders.
Closing month |  | 2026-09-30 |  | As of | 2026-10-08
No. | Area | Task | Owner | Reviewer | Working day | Due date | Status | Completed on | Days late | Flag | Notes
1 | Cash & bank | Bank reconciliation for all accounts | Accountant 1 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
2 | Cash & bank | Toll cash deposit vs daily collection reconciliation | Accountant 2 | Finance manager | 1 | 2026-10-01 | Done | 2026-10-01 | 0
3 | Cash & bank | FASTag / electronic toll settlement reconciliation | Accountant 3 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
4 | Cash & bank | Fixed deposit and treasury interest accrual | Accountant 4 | Finance manager | 1 | 2026-10-01 | Done | 2026-10-06 | 2 | Done late
5 | Revenue | Toll revenue cut-off and booking (plaza-wise) | Accountant 1 | Finance manager | 1 | 2026-10-01 | Done | 2026-10-01 | 0
6 | Revenue | Exempt and discounted traffic review | Accountant 2 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
7 | Revenue | Other income (advertising, wayside, rentals) invoicing | Accountant 3 | Finance manager | 1 | 2026-10-01 | Done | 2026-10-01 | 0
8 | Revenue | Annuity / O&M receivable booking (HAM SPVs) | Accountant 4 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
9 | Payables & accruals | Month-end provisions for unbilled services | Accountant 1 | Finance manager | 0 | 2026-09-30 | Done | 2026-09-30 | 0
10 | Payables & accruals | Reverse last month's provisions | Accountant 2 | Finance manager | 1 | 2026-10-01 | Done | 2026-10-01 | 0
11 | Payables & accruals | Prepaid expenses amortisation | Accountant 3 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
12 | Payables & accruals | Vendor ledger scrutiny and debit balances | Accountant 4 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
13 | Payables & accruals | O&M contractor bill certification | Accountant 1 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
14 | Fixed assets | Capitalise completed work (CWIP to assets) | Accountant 2 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
15 | Fixed assets | Depreciation / amortisation run (books) | Accountant 3 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
16 | Fixed assets | Major maintenance provision / MMRA review | Accountant 4 | Finance manager | 4 | 2026-10-07 | In progress |  |  | OVERDUE
17 | Ind AS adjustments | Ind AS 116 lease entries (interest, ROU depreciation) | Accountant 1 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
18 | Ind AS adjustments | Ind AS 109 ECL review on receivables | Accountant 2 | Finance manager | 4 | 2026-10-07 | In progress |  |  | OVERDUE
19 | Ind AS adjustments | Effective interest rate (EIR) on borrowings | Accountant 3 | Finance manager | 3 | 2026-10-06 | Done | 2026-10-06 | 0
20 | Ind AS adjustments | Deferred tax workings (quarter-end) | Accountant 4 | Finance manager | 5 | 2026-10-08 | In progress
21 | Tax & statutory | TDS deduction review and payment | Accountant 1 | Finance manager | 5 | 2026-10-08 | In progress
22 | Tax & statutory | GST output and input reconciliation (GSTR-2B vs books) | Accountant 2 | Finance manager | 6 | 2026-10-09 | Not started
23 | Tax & statutory | GSTR-1 / GSTR-3B filing support | Accountant 3 | Finance manager | 8 | 2026-10-13 | Not started
24 | Tax & statutory | Advance tax workings (instalment months) | Accountant 4 | Finance manager | 6 | 2026-10-09 | Not started
25 | Intercompany & InvIT | Interest on InvIT loans to SPVs: accrual and confirmation | Accountant 1 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
26 | Intercompany & InvIT | Intercompany balance confirmation (SPV / InvIT / HoldCo) | Accountant 2 | Finance manager | 4 | 2026-10-07 | In progress |  |  | OVERDUE
27 | Intercompany & InvIT | Investment manager / project manager fee accrual | Accountant 3 | Finance manager | 2 | 2026-10-05 | Done | 2026-10-05 | 0
28 | Intercompany & InvIT | NDCF working (quarter-end) | Accountant 4 | Finance manager | 7 | 2026-10-12 | Not started
29 | Reporting | Trial balance review and flux analysis | Accountant 1 | Finance manager | 5 | 2026-10-08 | In progress
30 | Reporting | Budget vs actual and commentary | Accountant 2 | Finance manager | 6 | 2026-10-09 | Not started
31 | Reporting | DSCR / covenant computation for lenders | Accountant 3 | Finance manager | 7 | 2026-10-12 | Not started
32 | Reporting | MIS pack to management | Accountant 4 | Finance manager | 7 | 2026-10-12 | Not started
33 | Reporting | Close sign-off by finance head | Accountant 1 | Finance manager | 8 | 2026-10-13 | Not started
Formulas:
Due date = IF(OR([Task]="",[Working day]=""),"",IF([Working day]>=1,WORKDAY(Settings!$C5,[Working day],Settings!$B11:B50),WORKDAY(Settings!$C7+1,[Working day]-1,Settings!$B11:B50)))
Days late = IF(OR([Due date]="",[Status]<>"Done",[Completed on]=""),"",MAX(0,NETWORKDAYS([Due date],[Completed on],Settings!$B11:B50)-1))

## Dashboard
Close Progress
For computation and reconciliation assistance only; not a substitute for formal statutory audit or legal tax advice.
Area | Tasks | Done | Not applicable | In progress | Not started | Overdue | % complete
Cash & bank | 4 | 4 | 0 | 0 | 0 | 0 | 100%
Revenue | 4 | 4 | 0 | 0 | 0 | 0 | 100%
Payables & accruals | 5 | 5 | 0 | 0 | 0 | 0 | 100%
Fixed assets | 3 | 2 | 0 | 1 | 0 | 1 | 66.67%
Ind AS adjustments | 4 | 2 | 0 | 2 | 0 | 1 | 50%
Tax & statutory | 4 | 0 | 0 | 1 | 3 | 0 | 0%
Intercompany & InvIT | 4 | 2 | 0 | 1 | 1 | 1 | 50%
Reporting | 5 | 0 | 0 | 1 | 4 | 0 | 0%
TOTAL | 33 | 19 | 0 | 6 | 8 | 3 | 57.58%
Checks
Every task has an area from this list | [6 empty] | OK
Every task has a status | [6 empty] | OK
Every Done task has a completion date | [6 empty] | OK